## Bug Report
HamroBazar — Bug Report by Module
App: https://hamrobazaar.com ¦ Generate: npm run qa:bugs ¦ Last full test run: 26 passed, 5 failed, 1 skipped
Bug ID | Module | Feature | Title | Severity | Priority | Status | Type | Related Test Case(s) | Steps to Reproduce | Expected Result | Actual Result | Environment | Browser | Evidence | Reported By | Report Date | Comments
BUG-HB-001 | Chat | Start a chat | Chat feature shows "Under construction" instead of opening chat | Major | P0 | Open | Functional | — | 1. Open https://hamrobazaar.com 2. Open any ad detail page 3. Click "Start a chat" 4. Observe dialog content | Chat opens or prompts user to sign in and start messaging the seller. | Modal appears with message "Under construction" and "We are working on the chat feature." User must click "Got it" to dismiss. | Production — https://hamrobazaar.com | Chrome (Chromium) | tests/09-chat.spec.js; playwright-report | Playwright QA | 2026-06-16 | Automated tests pass because they assert the placeholder dialog. Feature is not live for buyers/sellers.
BUG-HB-002 | Chat | Chat page | Dedicated /chat page does not provide messaging for guests | Minor | P2 | Open | Functional | — | 1. Open https://hamrobazaar.com/chat (not signed in) 2. Review page content | Guest sees chat inbox or clear path to sign in and use chat. | Page loads but only shows Sign in option; underlying chat feature is under construction. | Production — https://hamrobazaar.com | Chrome (Chromium) | tests/09-chat.spec.js | Playwright QA | 2026-06-16 | Related to BUG-HB-001. Consider hiding chat entry points until feature ships.
BUG-HB-003 | Auth | Phone validation | Login phone field shows invalid state for valid 10-digit Nepal mobile number | Major | P0 | Open | Validation | C15, C19 | 1. Go to https://hamrobazaar.com/login 2. Enter phone: 9877692345 3. Enter any password 4. Tab out of phone field or click Log In | Valid 10-digit Nepal mobile (98xxxxxxxx) is accepted without error styling. | Phone input displays red error border / invalid state even though the number matches expected Nepal mobile format. | Production — https://hamrobazaar.com | Chrome (Chromium) | phone-validation.png | Manual QA | 2026-06-16 | User reported "invalid number" UI. Verify country scrollable country picker or libphonenumber rules reject this prefix.
BUG-HB-004 | Auth | Login submit | Login request blocked by reCAPTCHA before credentials are verified | Minor | P1 | Open | Security / UX | C19 | 1. Go to /login 2. Fill valid phone and password 3. Click Log In without completing reCAPTCHA | Clear message that captcha is required, or login API validates credentials after captcha. | No HamroBazar auth API call is sent; user remains on /login with no server-side invalid-credential feedback. | Production — https://hamrobazaar.com | Chrome (Chromium) | tests/04-auth.spec.js; network trace during manual run | Playwright QA | 2026-06-16 | Expected bot protection, but blocks automated regression of C19 (invalid login feedback).
BUG-HB-005 | Auth | Invalid login feedback | Cannot verify error message for wrong credentials (blocked by captcha) | Minor | P1 | Blocked | Functional | C19 | 1. Go to /login 2. Enter wrong phone/password 3. Complete captcha 4. Submit | Clear error message; user stays on login page. | Manual test not completed — reCAPTCHA prevents unattended verification. | Production — https://hamrobazaar.com | Chrome / manual | HamroBazar-Test-Cases-Detailed.csv (C19 Pending) | QA Team | 2026-06-16 | Retest manually in browser with captcha completed.
BUG-HB-006 | Header | Navigation links | Duplicate "Home" links on page (utility bar + logo) | Minor | P2 | Fixed | UX / Accessibility | C2, S9 | 1. Open homepage or /FAQ 2. Inspect header 3. Search DOM for links named "Home" | Single unambiguous Home navigation control in the active header region. | Two links resolve to Home: utility-bar-home-link and navbar-logo-link (both href="/"). Automation cannot click by role without ambiguity. | Production — https://hamrobazaar.com | Chrome (Chromium) | tests/05-header.spec.js; pages/HeaderPage.js uses utility-bar-home-link | Playwright QA | 2026-06-16 | Fixed in automation via getByTestId("utility-bar-home-link"). Website still has duplicate Home links for users.
BUG-HB-007 | Header | Contact link | Duplicate "Contact us" links visible (utility bar and footer) | Minor | P2 | Fixed | UX / Accessibility | S9, C2 | 1. Open homepage 2. Scroll so footer is visible 3. Locate Contact us links | One Contact link per navigation region, or distinct labels (e.g. header vs footer). | getByRole("link", { name: /Contact us/i }) matches utility-bar-contact-link and footer-link-contact-us simultaneously. | Production — https://hamrobazaar.com | Chrome (Chromium) | tests/05-header.spec.js; tests/06-footer.spec.js; pages use data-testid | Playwright QA | 2026-06-16 | Fixed in automation: HeaderPage uses utility-bar-contact-link; FooterPage uses footer-link-contact-us.
BUG-HB-008 | Navigation | Ad listing from homepage | Specific trending ad "Iphone 13 Fresh" not always present on homepage | Trivial | P2 | Fixed | Content / Test data | S6 | 1. Open homepage 2. Search for listing titled "Iphone 13 Fresh" | Smoke test ad remains available or test uses dynamic first ad link. | Link /Iphone 13 Fresh/i not found on homepage during test run; navigation spec failed. | Production — https://hamrobazaar.com | Chrome (Chromium) | tests/03-navigation.spec.js; tests/08-ad-detail.spec.js uses dynamic selector | Playwright QA | 2026-06-16 | Homepage listings rotate. Fixed in tests/03-navigation.spec.js using dynamic /detail/ link.
BUG-HB-009 | Search | Empty search | Empty search submit behavior not verified | Trivial | P1 | Pending | Functional | C8 | 1. Focus search box on homepage 2. Submit with empty query | No crash; stay on page or show helpful message. | Not yet tested manually. | Production — https://hamrobazaar.com | Manual | HamroBazar-QA-Sheet.csv (C8 Manual) | QA Team | 2026-06-16 | Add automated or manual result to close C8.
BUG-HB-010 | Search | Special characters | Special character and Nepali text search not verified | Trivial | P2 | Pending | Functional | C9 | 1. Search @#$ 2. Search Nepali text sample 3. Observe results | No error page; application remains usable. | Not yet tested manually. | Production — https://hamrobazaar.com | Manual | HamroBazar-QA-Sheet.csv (C9 Manual) | QA Team | 2026-06-16 | Low priority edge-case coverage.
BUG-HB-011 | Homepage | All Categories | All Categories menu behavior not verified | Trivial | P1 | Pending | Functional | C4 | 1. Open homepage 2. Click All Categories 3. Verify category list appears | Category menu or list opens. | Manual test pending. | Production — https://hamrobazaar.com | Manual | HamroBazar-Test-Cases-Detailed.csv (C4) | QA Team | 2026-06-16
BUG-HB-012 | Homepage | Latest uploads | Latest Uploads / Recommended section not verified | Trivial | P1 | Pending | Functional | C5 | 1. Scroll homepage 2. Locate Latest Uploads or Recommended section | Section visible with listings. | Manual test pending. | Production — https://hamrobazaar.com | Manual | HamroBazar-Test-Cases-Detailed.csv (C5) | QA Team | 2026-06-16
BUG-HB-013 | Listing | Contact seller | Seller contact / call option on ad detail not verified | Trivial | P1 | Pending | Functional | C14 | 1. Open any ad detail page 2. Look for contact or call button | Seller contact option is visible and actionable. | Manual test pending. | Production — https://hamrobazaar.com | Manual | HamroBazar-Test-Cases-Detailed.csv (C14) | QA Team | 2026-06-16
BUG-HB-014 | Global | Error boundary | Intermittent "Something went wrong — critical error occurred" page | Critical | P0 | Open | Functional / Stability | S1, C1 | 1. Browse https://hamrobazaar.com 2. Navigate pages or run automated tests 3. Observe full-page error: "Something went wrong" / "A critical error occurred. We apologize for the inconvenience." | All key pages load without generic crash/error boundary screen. | Users reported generic critical error page. Main routes currently load OK in automation; error may be intermittent or tied to specific actions (login, chat, certain ads). | Production — https://hamrobazaar.com | Chrome (Chromium) / Safari | tests/10-critical-error.spec.js; user report; HamroBazar-Bug-Report.csv | Manual QA / Playwright QA | 2026-06-17 | Automated guard added in tests/10-critical-error.spec.js. If error appears, note exact URL and steps; report to support@hamrobazar.com.
SUMMARY BY MODULE
Auth | 3 issue(s) — 2 open
Chat | 2 issue(s) — 2 open
Global | 1 issue(s) — 1 open
Header | 2 issue(s) — 0 open
Homepage | 2 issue(s) — 0 open
Listing | 1 issue(s) — 0 open
Navigation | 1 issue(s) — 0 open
Search | 2 issue(s) — 0 open
PRIORITY LEGEND
P0 | Critical — blocks release / core flow broken
P1 | Important — fix before release if possible
P2 | Low — can defer

## By Module
Module | Bug IDs
Auth | BUG-HB-003, BUG-HB-004, BUG-HB-005
Chat | BUG-HB-001, BUG-HB-002
Global | BUG-HB-014
Header | BUG-HB-006, BUG-HB-007
Homepage | BUG-HB-011, BUG-HB-012
Listing | BUG-HB-013
Navigation | BUG-HB-008
Search | BUG-HB-009, BUG-HB-010